## First Five Year Program (prop)
| DRAFT South Bay Measure R Five-Year Funding Allocation | [14 empty] | DRAFT 5-Year Allocation (in '000s)
[16 empty] | 25899.5 |  | 35901.5 |  | 35899.872 |  | 57699.75 |  | 18699 |  | 174099.622
| Draft for Discussion: 4/21/2011 | [14 empty] | 25900 |  | 35900 |  | 35900 |  | 57700 |  | 18700 |  | 174100
[16 empty] | 0.5 |  | -1.5 |  | 0.128 |  | 0.25 |  | 1
| Identification |  | Location |  |  | Description |  | Status | [7 empty] | FY 2011/12 |  | FY 2012/13 |  | FY 2013/14 |  | FY 2014/15 |  | FY 2015/16 |  | Total
GIS Number | ID | Type | Facility | Limits | City/County |  | Source | Lead Agency | Document | MOU: Design & ROW | MOU: Construction | Cost Estimate | Funding | Committed Funds | Shortfall / Measure R Request | Proj. Dev. | Const | Proj. Dev. | Const | Proj. Dev. | Const | Proj. Dev. | Const | Proj. Dev. | Const
|  | Contingency |  |  |  | Early Action Contingency | [9 empty] | 5000 | [9 empty] | 5000
|  | Contingency |  |  |  | Program Contingency | [9 empty] | 474 |  | 800 |  |  |  | 750 |  | 2353
|  | Program Management |  |  |  | Program Development and Oversight | [13 empty] | 192 |  | 830 |  | 800
|  | Program Management |  |  |  | Program Administration | [13 empty] | 138 |  | 142 |  | 146
|  | Proj. Development |  |  |  | Strategic Positioning Reserve Funds | [15 empty] | 5300 |  | 12900
| F38 | Auxiliary lane | I-110 | Southbound: I-405 to Del Amo Boulevard Undercrossing | County | PSR: Widened southbound from three to four lanes | SBCCOG List | Caltrans | Concept | Yes | [5 empty] | 150
| B7 | Arterial & Ramp | I-405 | at 182nd St. / Crenshaw Boulevard | Torrance | PSR and PAED: Bundled Projects Group 7: F20, F21, F22, F23 | SBCCOG List | Caltrans | Concept | Yes | [5 empty] | 1700
| B7 | Arterial & Ramp | I-405 | at 182nd St. / Crenshaw Boulevard | Torrance | PSR and PAED: Bundled Projects Group 7: F20, F21, F22, F23 | SBCCOG List | Torrance | Concept | Yes | [5 empty] | 300
| F58 | Intersc. | I-405 | at I-110 | County | PSR: Construct new NB I-405 to SB I-110 connector, possibly a flyover ramp. | SBCCOG List | Caltrans | Concept | Yes | [5 empty] | 1000
| B15 |  | SR-1 | from Imperial Highway to Crenshaw Boulevard |  | Bundle: Implement PCH Study Recommendations | [19 empty] | 0
102 | F39 | Arterial | Sepulveda Boulevard | from Imperial Highway to El Segundo Boulevard | El Segundo | PCH Study Improvements: Implement PCH Study Recommendations (8) | PCH Study (2009) | El Segundo | Concept |  |  | 400000 | No Funds | 0 | 400000 | [6 empty] | 40 | 360 |  |  | 400
39 | F45 | Arterial | Pacific Coast Highway | from Artesia Boulevard to Anita Street | Hermosa Beach | PCH Study Improvements: Implement PCH Study Recommendations | PCH Study (2009) | Hermosa Beach | Concept | Yes | Yes | 240000 | No Funds | 0 | 240000 | 24 | 216 | [8 empty] | 240
161 | F49 | Arterial | Pacific Coast Highway | from Palos Verdes Boulevard to Crenshaw Boulevard | Torrance | PCH Study Improvements: Implement PCH Study Recommendations (8) | PCH Study (2009) | Torrance | Concept | Yes | Yes | 1840000 | No Funds | 0 | 1840000 | 184 | 1656 | [8 empty] | 1840
8 | F46 | Arterial | Pacific Coast Highway | from Anita Street to Palos Verdes Boulevard | Redondo Beach | PCH Study Improvements: Implement PCH Study Recommendations (11) | PCH Study (2009) | Redondo Beach | Concept | Yes | Yes | 1400000 | No Funds | 0 | 1400000 | 140 | 1260 | [8 empty] | 1400
116 | F41 | Arterial | Sepulveda Boulevard | from 33rd Street to south of Rosecrans Avenue | Manhattan Beach | Add one northbound lane by widening bridge no. 53-62 | SBCCOG List | Manhattan Beach | City advertised for conceptual design 8/10, 2013/2014 construction |  |  | 19829645 | CFP: $6.8m City Funds: $3.916m | 10729645 | 9100000 |  |  |  | 4550 |  | 4550 |  |  |  |  | 9100
1 | F11 | Arterial | Rosecrans Avenue | From I-405 Southbound off-ramp to Isis Avenue | Hawthorne | Widen Rosecrans Avenue to accommodate southbound off-ramp receiving lane. | City | Hawthorne | Design 80%, City has ROW | No | Yes | 3500000 | $1.4 million from HSIP | 1400000 | 2100000 |  | 2100 | [8 empty] | 2100
107 | F42 | Intersc. | Sepulveda Boulevard | at Marine Avenue | Manhattan Beach | Add westbound dual left turns | City | Manhattan Beach | Design and Caltrans Permit complete, City has ROW | No | Yes | 500000 | No Funds | 265000 | 235000 |  | 235 | [8 empty] | 235
63 | FN 1 | ITS | Pacific Coast Highway and Parallel Arterials | From Imperial Highway to Artesia Boulevard | County, El Segundo, Hawthorne, Manhattan Beach | PCH North Corridor - Improve traffic operations and implement ITS Elements. North/South: Pacific Coast Higheway, Aviation Boulevard. East/West: Imperial Highway, El Segundo Blvd., Rosecrans Ave., Manhattan Beach Blvd., Artesia Blvd. | Iteris Team | Caltrans | Concept |  |  | 6000000 | No Funds | 0 | 6000000 |  |  | 600 | 3400 |  | 2000 |  |  |  |  | 6000
16 | FN 2 | ITS | Pacific Coast Highway and Parallel Arterials | Palos Verde Blvd to I-110 | County, Lomita, Torrance | PCH South Corridor-- Torrance Area ATMS. Improve traffic operations and implement ITS Elements | Iteris Team | Caltrans | Concept |  |  | 3000000 | No Funds | 0 | 3000000 |  |  | 300 | 2700 | [6 empty] | 3000
60 | N6 | ITS | Various | Various | Inglewood | 4th Phase of Citywide ITS Master Plan (central computer system with fiber optic interconnection linking all signalized intersections for two-way communications) | SBCCOG List | Inglewood | Concept Phase | Yes |  | 3500000 | No funds | 0 | 3500000 | 300 |  |  | 3200 | [6 empty] | 3500
97 | N32 | Arterial | Del Amo Boulevard | from Normandie Boulevard to Vermont Avenue | County | Reconstruct and widen from one lane in each direction to two lanes in each direction | SBCCOG List | County | Preliminary Design Complete | Yes |  | 29920250 | $2.4m in SAFTEA-Lu and $600k in Local Funds | 3000000 | 26920250 |  | 500 |  | 500 |  | 1000 |  | 24920.25 |  |  | 26920.25
88 | F29 | ITS | I-405 & Arterial Roadways | Imperial Highway to Carson on I-405 and Parallel Arterials | Carson, County, Lawndale, Hawthorne, Redondo Beach, Torrance | I-405 Congestion Relief Corridor: Ramp and Arterial ITS Integration Freeway/Arterial/Interchange Corridor System Management - Roasecrans Ave., Manhattan Beach Blvd., Artesia Blvd., Inglewood Ave., Hawthorne Blvd., Crenshaw Blvd. | Iteris Team | SBCCOG | Concept |  |  | 7000000 | No Funds | 0 | 7000000 |  |  | 700 | 4300 |  | 2000 |  |  |  |  | 7000
| B11 |  | Aviation Boulevard | Aviation Boulevard Improvement Projects | County, El Segundo, Manhattan Beach, Redondo Beach, Hermosa Beach | Phase 1: Intersection Improvements: N12, N13, N14, N17, N56 (fully funded County ITS project), N57, N58 | Various | [18 empty] | 0
162 | N13 | Intersc. | Aviation Boulevard | at Marine Avenue | Manhattan Beach | Add dual southbound left-turn lanes. Aviation Boulevard Phase 1: Intersection Projects | SBCCOG List | Manhattan Beach | Preliminary Design |  |  | 1500000 | No Funds | 0 | 1500000 |  |  |  |  | 150 | 1350 |  |  |  |  | 1500
| N14 | Intersc. | Aviation Boulevard | at Marine Avenue | Hawthorne | Construct westbound right-turn lane. Aviation Boulevard Phase 1: Intersection Projects | City | Hawthorne | Concept, ROW required |  |  | 900000 | Local: $300k | 300000 | 600000 |  |  |  | 600 | [6 empty] | 600
| N58 | Intersc. | Aviation Boulevard | at Artesia Boulevard | Redondo Beach | Construct northbound right-turn lane. Aviation Boulevard Phase 1: Intersection Projects | City | Redondo Beach | Preliminary Design Complete, City has approval to take ROW | No | Yes | 847000 | No Funds | 0 | 847000 |  | 847 | [8 empty] | 847
| N57 | Intersc. | Aviation Boulevard | at Artesia Boulevard | Manhattan Beach | Construct southbound right-turn lane. Aviation Boulevard Phase 1: Intersection Projects |  | Manhattan Beach | Concept |  |  | 1500000 | No Funds, ROW dedication issue | 0 | 1500000 | [8 empty] | 150 | 1350 | 1500
| N17 | Intersc. | Aviation Boulevard | at Artesia Boulevard | Redondo Beach | Construct eastbound right-turn lane. Aviation Boulevard Phase 1: Intersection Projects | Circulation Element Update | Redondo Beach | Concept | No | Yes | 22000 | No Funds | 0 | 22000 |  | 22 | [8 empty] | 22
59 | F60 | ITS | I-405, I-110, I-105, SR-91 | at freeway ramp/arterial signalized intersections | Carson, County, El Segundo, Hawthorne, Inglewood, Los Angeles, Lawndale, Redondo Beach, Torrance | Coordinate freeway ramp/arterial intersections with arterial corridors. (e.g. NB I-405 Off-Ramp at Artesia Boulevard, SB I-110 Off-Ramp at Pacific Coast Highway) | Iteris Team | Caltrans | Concept | Yes | Yes | 5000000 | No Funds | 0 | 5000000 | 500 | 4500 | [8 empty] | 5000
65 | N22 | Arterial | Inglewood Avenue | from 156th Street to I-405 southbound on-ramp | Lawndale | Extension of Phase 2 widening to I-405 southbound ramp | City | Lawndale | Concept | Yes |  | 500000 | No Funds | 0 | 500000 |  | 100 |  | 400 | [6 empty] | 500
28 | F43 | Intersc. | Sepulveda Boulevard | at Manhattan Beach Boulevard | Manhattan Beach | Add northbound, westbound and eastbound dual left turn lanes and southbound right-turn lane | SBCCOG List | Manhattan Beach | Conceptual design and traffic analysis complete |  |  | 1480000 | $500k in City funds | 500000 | 980000 | [5 empty] | 980 |  |  |  |  | 980
66 | F51 | Intersc. | Pacific Coast Highway | at Hawthorne Boulevard | Torrance | Add northbound, eastbound, and westbound right-turn lane, add eastbound left-turn, signal upgrades | City Traffic Study | Torrance | Preliminary Design Complete; PSR (2002) | Yes |  | 19600000 | No Funds | 0 | 19600000 | 1300 |  |  |  | 300 |  |  | 18000 |  |  | 19600
31 | N25 | ITS | Various | Citywide | Lawndale | Traffic Signal Improvements Citywide | SBCCOG List | Lawndale | Concept |  |  | 1500000 | No Funds | 0 | 1500000 |  |  | 150 |  |  |  |  | 1350 |  |  | 1500
30 | F47 | Intersc. | Pacific Coast Highway | at Torrance Boulevard | Redondo Beach | Add northbound right-turn lane | City | Redondo Beach | Concept | Yes |  | 585000 | No Funds | 0 | 585000 | 58.5 |  |  | 526.5 | [6 empty] | 585
67 | F48 | Intersc. | Pacific Coast Highway | at Palos Verdes Boulevard | Redondo Beach | Install westbound right-turn lane | City | Redondo Beach | Concept | Yes |  | 320000 | No Funds | 0 | 320000 | 32 |  |  | 288 | [6 empty] | 320
| N34 | Arterial | Sepulveda Boulevard | from Alameda Street to ICTF Driveway | Carson | Widen from four lanes to six lanes, rehabilitate bridge. | SBCCOG List, 2008 RTIP | Carson | Bridge funds programmed for 2014/2015 |  |  | 6000000 | Fed: $1.217m, Agency: 3.625 million | 4842000 | 1158000 |  |  |  | 1158 | [6 empty] | 1158
70 | F44 | Intersc. | Pacific Coast Highway | at Aviation Boulevard | Hermosa Beach | Add southbound dual left turn lanes | SBCCOG List | Hermosa Beach | Concept, ROW required (Park) |  |  | 1000000 | No Funds | 0 | 1000000 | [9 empty] | 1000 | 1000
| N42 | Arterial | Rosecrans Avenue | from Vermont Avenue to Crenshaw Boulevard | Gardena | Install median, left turn pockets, intersection upgrade. Coordinated with County TSSP project. | SBCCOG List | Gardena | PSRE | Yes |  | 5140000 | No Funds | 0 | 5140000 | 300 |  | 317 |  |  | 4523 |  |  |  |  | 5140
| N46 | Arterial | Vista Del Mar | north of southern City Limit | El Segundo | Roadway safety improvements: realign S-Curve | SBCCOG List | El Segundo | Concept |  |  | 1500000 | No Funds | 0 | 1500000 |  |  | 150 |  |  |  |  | 1350 |  |  | 1500
| F2 | Ramp | I-405 | at Manchester Blvd. | Inglewood | Early Action: Improve turn radii at northbound I-405 off-ramp at Manchester Boulevard | SBCCOG List | Caltrans/City | Concept | No | Yes | 186000 | No Funds | 0 | 186000 |  | 186 | [8 empty] | 186
| P4 | Park & Ride | Torrance Regional Transit Center | 465 Crenshaw Boulevard | Torrance | Construct a regional Transit Center including an 8 bus berth transit center building, a kiss-n-ride passenger drop-off, and a park-and-ride vehicle lot for 250 vehicles for the initial parking space provision | SBCCOG List | Torrance | In Design |  |  | 21000000 | No Funds | 0 | 21000000 |  |  |  | 10500 |  | 10500 |  |  |  |  | 21000
| N47 | Intersc. | Maple Avenue | at Sepulveda Boulevard | Torrance | Add southbound right-turn pocket | SBCCOG List | Torrance | Concept | Yes |  | 600000 | No Funds | 0 | 600000 | 60 |  |  | 540 | [6 empty] | 600
75 | N53 | Intersc. | Artesia Boulevard | at Western Avenue | Gardena, Torrance | Add westbound dual left turns. | City | Gardena | Concept | Yes |  | 675000 | No Funds | 0 | 675000 | 75 |  |  |  |  | 600 |  |  |  |  | 675
| N69 | Arterial | Maple Avenue | from Sepulveda Boulevard to Parkview Avenue | El Segundo | Improve signanage and roadway to provide a connection between northbound Sepulveda Boulevard and the eastbound I-105 ramps. | City | El Segundo | Concept | No | Yes | 2500000 | No Funds | 0 | 2500000 |  | 2500 | [8 empty] | 2500
33 | F56 | Intersc. | Western Avenue | at Palos Verdes Drive North | Lomita/Los Angeles | Intersection improvements | City | Lomita | Concept |  |  | 500000 | No Funds | 0 | 500000 |  |  | 50 |  |  | 500 |  |  |  |  | 550
| N67 | Arterial | Vermont Avenue | From Rosecrans Avenue to 182nd Street | Gardena | Addition of turn pockets, channelization, pavement upgrade, traffic signal improvements, and minor concrete work | City | Gardena | Concept | Yes |  | 2350000 | No Funds | 0 | 2350000 | 150 |  | 132 |  |  | 2068 |  |  |  |  | 2350
| N18 | Intersc. | Inglewood Avenue | at Manhattan Beach Boulevard | Redondo Beach | Add southbound right-turn lane south of railroad tracks to Manhattan Beach Boulevard | SBCCOG List | Redondo Beach | Preliminary Design Complete, ROW required |  |  | 5175000 | No Funds | 0 | 5175000 |  |  |  |  | 517.5 |  |  | 4657.5 |  |  | 5175
| F53 | Intersc. | Pacific Coast Highway | at Walnut | Lomita | Improve receiving lane of northern leg of intersection | City | Lomita | Concept |  |  | 400000 | No Funds | 0 | 400000 |  |  | 40 |  |  | 360 |  |  |  |  | 400
| N26 | Arterial | Hawthorne Boulevard | El Segundo Boulevard to Rosecrans Avenue | Hawthorne | Improve traffic signals; add left-turn pockets; pedestrian, transit & handicap access improvements. | SBCCOG List | Hawthorne | Concept |  |  | 9200000 | Metro: $2.916m, $2.11m Local Match | 5028628 | 4171372 | [5 empty] | 4171.372 |  |  |  |  | 4171.372
| N19 | Intersc. | Inglewood Avenue | at Manhattan Beach Boulevard | Redondo Beach | Install eastbound right-turn arrow | City | Redondo Beach | Concept | No | Yes | 30000 | No Funds | 0 | 30000 |  | 30 | [8 empty] | 30
[14 empty] | Estimated Total Early Action Program Cost | 141074622
[16 empty] | FY 2011 |  | FY 2012 |  | FY 2013 |  | FY 2014 |  | FY 2015
[16 empty] | 11747.5 | 14152 | 3239 | 32662.5 | 1297.5 | 34602.372 | 7062 | 50637.75 | 16349 | 2350
[16 empty] | Design | Const | Design | Const | Design | Const | Design | Const | Design | Const
[12 empty] | 143430250 |  | 15335628 |  | 45.36% | 54.64% | 9.022% | 90.98% | 3.614% | 96.39% | 12.24% | 87.76% | 87.43% | 12.57%
[24 empty] | 174099.622 |  | 146124.622