## Reporting
LEAD AGENCY | PROJECT | PROJECT ID | ITERIS CONTACT | Most recent contact date | LAST ACTION DATE | DATE TECH. ASST REQ | EST TECH. ASST COSTS | ACTUAL TECH ASST. TO DATE | FA EXECUTION DATE | DATE FA EXECUTED | PROJECT Funding agreement(s) STATUS | Iteris Assistance Needed?
CARSON | Sepulveda Blvd. | N34 | Farokh Abulfathi | [7 empty] | No action taken | tbd
EL SEGUNDO | Maple Avenue | N69 | Maryam Jonas |  | June | [5 empty] | Received Sample MOU from Metro - Could do it in house | tbd
GARDENA | Rosecrans Avenue | N42 | John Felix |  | June | [5 empty] | Submitted to Metro the required attachments of the city's MOU | no
GARDENA | Artesia Blvd | N53 | John Felix |  | June | [5 empty] | Submitted to Metro the required attachments of the city's MOU | no
GARDENA | Vermont Ave | N67 | John Felix |  | June | [5 empty] | Submitted to Metro the required attachments of the city's MOU | no
HAWTHORNE | Rosecrans Avenue | F11 | Akbar Farokhi | [7 empty] | Waiting for MOU for construction from Metro | yes
HAWTHORNE | Hawthorne Blvd | N26 | Akbar Farokhi | [7 empty] | Waiting for MOU for PE from Metro | yes
HAWTHORNE | Aviation Blvd at Marine Avenue | N14 | Akbar Farokhi | [7 empty] | Waiting for MOU for PE from Metro | yes
HERMOSA BEACH | PCH between Anita St. & Artesia Blvd | F45 | Frank Sentano | [7 empty] | No action taken | yes
HERMOSA BEACH | PCH at Aviation Blvd | F44 | Frank Sentano | [7 empty] | No action taken | yes
INGLEWOOD | ITS Phase IV | N6 | Chad Sweet | 2011-06-23 | [6 empty] | No action taken | yes
LAWNDALE | ITS PROJECTS |  | Marlene Miyoshi | [7 empty] | No-action taken | yes
LOMITA | Miscellaneous projects | F53 | Tom Shahbazi | [7 empty] | No action taken | yes
MANHATTAN BEACH | Sepulveda at Marine | F42 | Steve Finton | [7 empty] | No action taken | yes
MANHATTAN BEACH | Sepulveda Blvd. Bridge widening | F41 | Steve Finton | [7 empty] | No action taken | tbd
MANHATTAN BEACH | Aviation at Marine | N13 | Steve Finton | [7 empty] | No action taken | tbd
MANHATTAN BEACH | Aviation at Artesia | N57 | Steve Finton | [7 empty] | No action taken | tbd
MANHATTAN BEACH | Sepulveda at Manhattan Beach | F43 | Steve Finton | [7 empty] | No action taken | tbd
REDONDO BEACH | Aviation at Artesia-NB right turn lane | N58 | John Mate | [7 empty] | No action taken | yes
REDONDO BEACH | PCH between Anita St. & Palos Verdes | F46 | John Mate | [7 empty] | No action taken | yes
REDONDO BEACH | PCH at Torrance Ave | F47 | John Mate |  | June | [5 empty] | MOU process started-Metro has replied back to the draft in June | no
REDONDO BEACH | PCH at Palos Verdes | F48 | John Mate |  | June | [5 empty] | MOU process started-Metro has replied back to the draft in June | no
REDONDO BEACH | Inglewood Ave | N19 | John Mate |  | June | [5 empty] | MOU process started-Metro has replied back to the draft in June | no
REDONDO BEACH | Aviation at Artesia-EB right turn lane | N17 | John Mate |  | June | [5 empty] | MOU process started-Metro has replied back to the draft in June | no
TORRANCE | PCH/Hawthorne | F51 | Ted Semaan |  | July | [5 empty] | Preparing the MOU-Will need Caltrans/Tom Chow's help | yes
TORRANCE | Torrance Reg Transit Center | P4 | Ted Semaan |  | July | [5 empty] | Preparing the MOU-Will need "System Metrics Group" help | yes